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Summary :
During June, the program successfully achieved major milestones, highlighted by the graduation of our literacy and numeracy cohort and the preparation of new advanced training curricula. We maintained our commitment to inclusivity across all active language groups, serving a balanced demographic of host communities and internally displaced persons (IDPs), including youth groups. Active community networking and localized awareness campaigns were a primary focus this month, significantly expanding our institutional reach. Furthermore, high demand for our vocational programs was reflected in a substantial waiting list for upcoming cycles, while the tangible impact of our training was demonstrated by immediate employment outcomes for recent graduates.

# Act. 1.2 Training on basic skills
The training activities for June were distributed as follows:
Course Completions & Graduations:
 Literacy & Numeracy Group: We successfully graduated a cohort of 17 beneficiaries, all of whom are IDPs. This group was carried over from the previous month's reporting cycle to complete their remaining 18 sessions and have now officially concluded the course.
Ongoing Language & Basic Skills Groups:
 Turkish Language (Group A - Basic Level): This group consists of 9 female beneficiaries, all of whom are IDPs. They are continuing their coursework and progressing well.
 Turkish Language (Group B - Basic Level): This group consists of 9 beneficiaries (5 male, 4 female). The demographic includes 2 IDPs and 7 host community members.
 English Language (Starter Level): This young demographic group consists of 9 beneficiaries aged 13–17, all from the host community. They have successfully completed 10 sessions to date.
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Highlights of the month: 


· Employment Success Stories: In a major success for our centre’s impact, two of our recent beneficiaries (one male and one female) successfully secured formal employment immediately after finishing their courses.
· High Community Demand: We opened registration for an upcoming Arabic language module, resulting in an overwhelming response of 70 applicants who have now been placed on the waiting list.
· Curriculum Development: Our team finalized comprehensive teaching materials for a new Web Development & Coding Course covering HTML, CSS, and JavaScript, which is scheduled to launch in July.
· Material Production: We successfully developed targeted awareness materials focused on child safety online, titled "The Misuse of the Internet by Children: How to Protect Themselves from Online Dangers."
· Awareness Sessions & Community Engagement:
· Field Awareness Campaign: We conducted a specialized protection and awareness session in Khanke tailored specifically for a group of displaced female IDPs.
· Institutional Coordination: To streamline upcoming activities and strengthen local partnerships, our team conducted three strategic stakeholder visits this month:

1. The Women's Union Center in Sumel.
2. Rasti Primary School in Khanke.
3. The Peace and Human Development Organization (PDO) in Khanke.

Challenges and amendments: 
Academic Exam Period: A primary challenge faced this month was the scheduling conflict with school final exams. Many of our younger beneficiaries were busy stduying for and taking their exams, which temporarily restricted their ability to attend and fully participate in the scheduled center activities.

Lessons Learned 

 Economic Impact of Training: The immediate employment of two graduates proves that our language and skill modules directly align with local market needs, validating the economic utility of the project.

 Digital Training Demand: The massive registration numbers (70 applicants) for the Arabic course, combined with the upcoming coding class, highlight a shifting community preference toward digital literacy and professional language capacities.






Plan for next Month 

	#
	Activities/Output#
	due date

	1
	Web Development & Coding
	July 2026

	2
	Arabic Language
	July 2026
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