{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Лист1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Лист1","index":0,"n_rows":142,"n_cols":68,"rows_kept":142,"cut":false,"hidden":false,"merged":[[141,49,141,51],[141,52,141,54],[141,55,141,57],[141,58,141,60],[141,61,141,63],[141,64,141,66],[141,31,141,33],[141,34,141,36],[141,37,141,39],[141,40,141,42],[141,43,141,45],[141,46,141,48],[140,61,140,63],[140,64,140,66],[141,7,141,9],[141,10,141,12],[141,13,141,15],[141,16,141,18],[141,19,141,21],[141,22,141,24],[141,25,141,27],[141,28,141,30],[140,43,140,45],[140,46,140,48],[140,49,140,51],[140,52,140,54],[140,55,140,57],[140,58,140,60],[140,25,140,27],[140,28,140,30],[140,31,140,33],[140,34,140,36],[140,37,140,39],[140,40,140,42],[140,7,140,9],[140,10,140,12],[140,13,140,15],[140,16,140,18],[140,19,140,21],[140,22,140,24],[139,49,139,51],[139,52,139,54],[139,55,139,57],[139,58,139,60],[139,61,139,63],[139,64,139,66],[139,31,139,33],[139,34,139,36],[139,37,139,39],[139,40,139,42],[139,43,139,45],[139,46,139,48],[138,61,138,63],[138,64,138,66],[139,7,139,9],[139,10,139,12],[139,13,139,15],[139,16,139,18],[139,19,139,21],[139,22,139,24],[139,25,139,27],[139,28,139,30],[138,43,138,45],[138,46,138,48],[138,49,138,51],[138,52,138,54],[138,55,138,57],[138,58,138,60],[138,25,138,27],[138,28,138,30],[138,31,138,33],[138,34,138,36],[138,37,138,39],[138,40,138,42],[138,7,138,9],[138,10,138,12],[138,13,138,15],[138,16,138,18],[138,19,138,21],[138,22,138,24],[137,49,137,51],[137,52,137,54],[137,55,137,57],[137,58,137,60],[137,61,137,63],[137,64,137,66],[137,31,137,33],[137,34,137,36],[137,37,137,39],[137,40,137,42],[137,43,137,45],[137,46,137,48],[136,61,136,63],[136,64,136,66],[137,7,137,9],[137,10,137,12],[137,13,137,15],[137,16,137,18],[137,19,137,21],[137,22,137,24],[137,25,137,27],[137,28,137,30],[136,43,136,45],[136,46,136,48],[136,49,136,51],[136,52,136,54],[136,55,136,57],[136,58,136,60],[136,25,136,27],[136,28,136,30],[136,31,136,33],[136,34,136,36],[136,37,136,39],[136,40,136,42],[136,7,136,9],[136,10,136,12],[136,13,136,15],[136,16,136,18],[136,19,136,21],[136,22,136,24],[135,49,135,51],[135,52,135,54],[135,55,135,57],[135,58,135,60],[135,61,135,63],[135,64,135,66],[135,31,135,33],[135,34,135,36],[135,37,135,39],[135,40,135,42],[135,43,135,45],[135,46,135,48],[134,61,134,63],[134,64,134,66],[135,7,135,9],[135,10,135,12],[135,13,135,15],[135,16,135,18],[135,19,135,21],[135,22,135,24],[135,25,135,27],[135,28,135,30],[134,43,134,45],[134,46,134,48],[134,49,134,51],[134,52,134,54],[134,55,134,57],[134,58,134,60],[134,25,134,27],[134,28,134,30],[134,31,134,33],[134,34,134,36],[134,37,134,39],[134,40,134,42],[134,7,134,9],[134,10,134,12],[134,13,134,15],[134,16,134,18],[134,19,134,21],[134,22,134,24],[133,49,133,51],[133,52,133,54],[133,55,133,57],[133,58,133,60],[133,61,133,63],[133,64,133,66],[133,31,133,33],[133,34,133,36],[133,37,133,39],[133,40,133,42],[133,43,133,45],[133,46,133,48],[132,61,132,63],[132,64,132,66],[133,7,133,9],[133,10,133,12],[133,13,133,15],[133,16,133,18],[133,19,133,21],[133,22,133,24],[133,25,133,27],[133,28,133,30],[132,43,132,45],[132,46,132,48],[132,49,132,51],[132,52,132,54],[132,55,132,57],[132,58,132,60],[132,25,132,27],[132,28,132,30],[132,31,132,33],[132,34,132,36],[132,37,132,39],[132,40,132,42],[132,7,132,9],[132,10,132,12],[132,13,132,15],[132,16,132,18],[132,19,132,21],[132,22,132,24],[131,49,131,51],[131,52,131,54],[131,55,131,57],[131,58,131,60],[131,61,131,63],[131,64,131,66],[131,31,131,33],[131,34,131,36],[131,37,131,39],[131,40,131,42],[131,43,131,45],[131,46,131,48],[130,61,130,63],[130,64,130,66],[131,7,131,9],[131,10,131,12],[131,13,131,15],[131,16,131,18],[131,19,131,21],[131,22,131,24],[131,25,131,27],[131,28,131,30],[130,43,130,45],[130,46,130,48],[130,49,130,51],[130,52,130,54],[130,55,130,57],[130,58,130,60],[130,25,130,27],[130,28,130,30],[130,31,130,33],[130,34,130,36],[130,37,130,39],[130,40,130,42],[130,7,130,9],[130,10,130,12],[130,13,130,15],[130,16,130,18],[130,19,130,21],[130,22,130,24],[129,49,129,51],[129,52,129,54],[129,55,129,57],[129,58,129,60],[129,61,129,63],[129,64,129,66],[129,31,129,33],[129,34,129,36],[129,37,129,39],[129,40,129,42],[129,43,129,45],[129,46,129,48],[128,61,128,63],[128,64,128,66],[129,7,129,9],[129,10,129,12],[129,13,129,15],[129,16,129,18],[129,19,129,21],[129,22,129,24],[129,25,129,27],[129,28,129,30],[128,43,128,45],[128,46,128,48],[128,49,128,51],[128,52,128,54],[128,55,128,57],[128,58,128,60],[128,25,128,27],[128,28,128,30],[128,31,128,33],[128,34,128,36],[128,37,128,39],[128,40,128,42],[128,7,128,9],[128,10,128,12],[128,13,128,15],[128,16,128,18],[128,19,128,21],[128,22,128,24],[127,49,127,51],[127,52,127,54],[127,55,127,57],[127,58,127,60],[127,61,127,63],[127,64,127,66],[127,31,127,33],[127,34,127,36],[127,37,127,39],[127,40,127,42],[127,43,127,45],[127,46,127,48],[126,61,126,63],[126,64,126,66],[127,7,127,9],[127,10,127,12],[127,13,127,15],[127,16,127,18],[127,19,127,21],[127,22,127,24],[127,25,127,27],[127,28,127,30],[126,43,126,45],[126,46,126,48],[126,49,126,51],[126,52,126,54],[126,55,126,57],[126,58,126,60],[126,25,126,27],[126,28,126,30],[126,31,126,33],[126,34,126,36],[126,37,126,39],[126,40,126,42],[126,7,126,9],[126,10,126,12],[126,13,126,15],[126,16,126,18],[126,19,126,21],[126,22,126,24],[125,49,125,51],[125,52,125,54],[125,55,125,57],[125,58,125,60],[125,61,125,63],[125,64,125,66],[125,31,125,33],[125,34,125,36],[125,37,125,39],[125,40,125,42],[125,43,125,45],[125,46,125,48],[124,61,124,63],[124,64,124,66],[125,7,125,9],[125,10,125,12],[125,13,125,15],[125,16,125,18],[125,19,125,21],[125,22,125,24],[125,25,125,27],[125,28,125,30],[124,43,124,45],[124,46,124,48],[124,49,124,51],[124,52,124,54],[124,55,124,57],[124,58,124,60],[124,25,124,27],[124,28,124,30],[124,31,124,33],[124,34,124,36],[124,37,124,39],[124,40,124,42],[124,7,124,9],[124,10,124,12],[124,13,124,15],[124,16,124,18],[124,19,124,21],[124,22,124,24],[123,49,123,51],[123,52,123,54],[123,55,123,57],[123,58,123,60],[123,61,123,63],[123,64,123,66],[123,31,123,33],[123,34,123,36],[123,37,123,39],[123,40,123,42],[123,43,123,45],[123,46,123,48],[122,61,122,63],[122,64,122,66],[123,7,123,9],[123,10,123,12],[123,13,123,15],[123,16,123,18],[123,19,123,21],[123,22,123,24],[123,25,123,27],[123,28,123,30],[122,43,122,45],[122,46,122,48],[122,49,122,51],[122,52,122,54],[122,55,122,57],[122,58,122,60],[122,25,122,27],[122,28,122,30],[122,31,122,33],[122,34,122,36],[122,37,122,39],[122,40,122,42],[122,7,122,9],[122,10,122,12],[122,13,122,15],[122,16,122,18],[122,19,122,21],[122,22,122,24],[121,49,121,51],[121,52,121,54],[121,55,121,57],[121,58,121,60],[121,61,121,63],[121,64,121,66],[121,31,121,33],[121,34,121,36],[121,37,121,39],[121,40,121,42],[121,43,121,45],[121,46,121,48],[120,61,120,63],[120,64,120,66],[121,7,121,9],[121,10,121,12],[121,13,121,15],[121,16,121,18],[121,19,121,21],[121,22,121,24],[121,25,121,27],[121,28,121,30],[120,43,120,45],[120,46,120,48],[120,49,120,51],[120,52,120,54],[120,55,120,57],[120,58,120,60],[120,25,120,27],[120,28,120,30],[120,31,120,33],[120,34,120,36],[120,37,120,39],[120,40,120,42],[120,7,120,9],[120,10,120,12],[120,13,120,15],[120,16,120,18],[120,19,120,21],[120,22,120,24],[119,49,119,51],[119,52,119,54],[119,55,119,57],[119,58,119,60],[119,61,119,63],[119,64,119,66],[119,31,119,33],[119,34,119,36],[119,37,119,39],[119,40,119,42],[119,43,119,45],[119,46,119,48],[118,61,118,63],[118,64,118,66],[119,7,119,9],[119,10,119,12],[119,13,119,15],[119,16,119,18],[119,19,119,21],[119,22,119,24],[119,25,119,27],[119,28,119,30],[118,43,118,45],[118,46,118,48],[118,49,118,51],[118,52,118,54],[118,55,118,57],[118,58,118,60],[118,25,118,27],[118,28,118,30],[118,31,118,33],[118,34,118,36],[118,37,118,39],[118,40,118,42],[118,7,118,9],[118,10,118,12],[118,13,118,15],[118,16,118,18],[118,19,118,21],[118,22,118,24],[117,49,117,51],[117,52,117,54],[117,55,117,57],[117,58,117,60],[117,61,117,63],[117,64,117,66],[117,31,117,33],[117,34,117,36],[117,37,117,39],[117,40,117,42],[117,43,117,45],[117,46,117,48],[116,61,116,63],[116,64,116,66],[117,7,117,9],[117,10,117,12],[117,13,117,15],[117,16,117,18],[117,19,117,21],[117,22,117,24],[117,25,117,27],[117,28,117,30],[116,43,116,45],[116,46,116,48],[116,49,116,51],[116,52,116,54],[116,55,116,57],[116,58,116,60],[116,25,116,27],[116,28,116,30],[116,31,116,33],[116,34,116,36],[116,37,116,39],[116,40,116,42],[116,7,116,9],[116,10,116,12],[116,13,116,15],[116,16,116,18],[116,19,116,21],[116,22,116,24],[115,49,115,51],[115,52,115,54],[115,55,115,57],[115,58,115,60],[115,61,115,63],[115,64,115,66],[115,31,115,33],[115,34,115,36],[115,37,115,39],[115,40,115,42],[115,43,115,45],[115,46,115,48],[114,61,114,63],[114,64,114,66],[115,7,115,9],[115,10,115,12],[115,13,115,15],[115,16,115,18],[115,19,115,21],[115,22,115,24],[115,25,115,27],[115,28,115,30],[114,43,114,45],[114,46,114,48],[114,49,114,51],[114,52,114,54],[114,55,114,57],[114,58,114,60],[114,25,114,27],[114,28,114,30],[114,31,114,33],[114,34,114,36],[114,37,114,39],[114,40,114,42],[114,7,114,9],[114,10,114,12],[114,13,114,15],[114,16,114,18],[114,19,114,21],[114,22,114,24],[113,49,113,51],[113,52,113,54],[113,55,113,57],[113,58,113,60],[113,61,113,63],[113,64,113,66],[113,31,113,33],[113,34,113,36],[113,37,113,39],[113,40,113,42],[113,43,113,45],[113,46,113,48],[112,61,112,63],[112,64,112,66],[113,7,113,9],[113,10,113,12],[113,13,113,15],[113,16,113,18],[113,19,113,21],[113,22,113,24],[113,25,113,27],[113,28,113,30],[112,43,112,45],[112,46,112,48],[112,49,112,51],[112,52,112,54],[112,55,112,57],[112,58,112,60],[112,25,112,27],[112,28,112,30],[112,31,112,33],[112,34,112,36],[112,37,112,39],[112,40,112,42],[112,7,112,9],[112,10,112,12],[112,13,112,15],[112,16,112,18],[112,19,112,21],[112,22,112,24],[111,49,111,51],[111,52,111,54],[111,55,111,57],[111,58,111,60],[111,61,111,63],[111,64,111,66],[111,31,111,33],[111,34,111,36],[111,37,111,39],[111,40,111,42],[111,43,111,45],[111,46,111,48],[110,61,110,63],[110,64,110,66],[111,7,111,9],[111,10,111,12],[111,13,111,15],[111,16,111,18],[111,19,111,21],[111,22,111,24],[111,25,111,27],[111,28,111,30],[110,43,110,45],[110,46,110,48],[110,49,110,51],[110,52,110,54],[110,55,110,57],[110,58,110,60],[110,25,110,27],[110,28,110,30],[110,31,110,33],[110,34,110,36],[110,37,110,39],[110,40,110,42],[110,7,110,9],[110,10,110,12],[110,13,110,15],[110,16,110,18],[110,19,110,21],[110,22,110,24],[109,49,109,51],[109,52,109,54],[109,55,109,57],[109,58,109,60],[109,61,109,63],[109,64,109,66],[109,31,109,33],[109,34,109,36],[109,37,109,39],[109,40,109,42],[109,43,109,45],[109,46,109,48],[108,61,108,63],[108,64,108,66],[109,7,109,9],[109,10,109,12],[109,13,109,15],[109,16,109,18],[109,19,109,21],[109,22,109,24],[109,25,109,27],[109,28,109,30],[108,43,108,45],[108,46,108,48],[108,49,108,51],[108,52,108,54],[108,55,108,57],[108,58,108,60],[108,25,108,27],[108,28,108,30],[108,31,108,33],[108,34,108,36],[108,37,108,39],[108,40,108,42],[108,7,108,9],[108,10,108,12],[108,13,108,15],[108,16,108,18],[108,19,108,21],[108,22,108,24],[107,49,107,51],[107,52,107,54],[107,55,107,57],[107,58,107,60],[107,61,107,63],[107,64,107,66],[107,31,107,33],[107,34,107,36],[107,37,107,39],[107,40,107,42],[107,43,107,45],[107,46,107,48],[106,61,106,63],[106,64,106,66],[107,7,107,9],[107,10,107,12],[107,13,107,15],[107,16,107,18],[107,19,107,21],[107,22,107,24],[107,25,107,27],[107,28,107,30],[106,43,106,45],[106,46,106,48],[106,49,106,51],[106,52,106,54],[106,55,106,57],[106,58,106,60],[106,25,106,27],[106,28,106,30],[106,31,106,33],[106,34,106,36],[106,37,106,39],[106,40,106,42],[106,7,106,9],[106,10,106,12],[106,13,106,15],[106,16,106,18],[106,19,106,21],[106,22,106,24],[105,49,105,51],[105,52,105,54],[105,55,105,57],[105,58,105,60],[105,61,105,63],[105,64,105,66],[105,31,105,33],[105,34,105,36],[105,37,105,39],[105,40,105,42],[105,43,105,45],[105,46,105,48],[104,61,104,63],[104,64,104,66],[105,7,105,9],[105,10,105,12],[105,13,105,15],[105,16,105,18],[105,19,105,21],[105,22,105,24],[105,25,105,27],[105,28,105,30],[104,43,104,45],[104,46,104,48],[104,49,104,51],[104,52,104,54],[104,55,104,57],[104,58,104,60],[104,25,104,27],[104,28,104,30],[104,31,104,33],[104,34,104,36],[104,37,104,39],[104,40,104,42],[104,7,104,9],[104,10,104,12],[104,13,104,15],[104,16,104,18],[104,19,104,21],[104,22,104,24],[103,49,103,51],[103,52,103,54],[103,55,103,57],[103,58,103,60],[103,61,103,63],[103,64,103,66],[103,31,103,33],[103,34,103,36],[103,37,103,39],[103,40,103,42],[103,43,103,45],[103,46,103,48],[102,61,102,63],[102,64,102,66],[103,7,103,9],[103,10,103,12],[103,13,103,15],[103,16,103,18],[103,19,103,21],[103,22,103,24],[103,25,103,27],[103,28,103,30],[102,43,102,45],[102,46,102,48],[102,49,102,51],[102,52,102,54],[102,55,102,57],[102,58,102,60],[102,25,102,27],[102,28,102,30],[102,31,102,33],[102,34,102,36],[102,37,102,39],[102,40,102,42],[102,7,102,9],[102,10,102,12],[102,13,102,15],[102,16,102,18],[102,19,102,21],[102,22,102,24],[101,49,101,51],[101,52,101,54],[101,55,101,57],[101,58,101,60],[101,61,101,63],[101,64,101,66],[101,31,101,33],[101,34,101,36],[101,37,101,39],[101,40,101,42],[101,43,101,45],[101,46,101,48],[100,61,100,63],[100,64,100,66],[101,7,101,9],[101,10,101,12],[101,13,101,15],[101,16,101,18],[101,19,101,21],[101,22,101,24],[101,25,101,27],[101,28,101,30],[100,43,100,45],[100,46,100,48],[100,49,100,51],[100,52,100,54],[100,55,100,57],[100,58,100,60],[100,25,100,27],[100,28,100,30],[100,31,100,33],[100,34,100,36],[100,37,100,39],[100,40,100,42],[100,7,100,9],[100,10,100,12],[100,13,100,15],[100,16,100,18],[100,19,100,21],[100,22,100,24],[99,49,99,51],[99,52,99,54],[99,55,99,57],[99,58,99,60],[99,61,99,63],[99,64,99,66],[99,31,99,33],[99,34,99,36],[99,37,99,39],[99,40,99,42],[99,43,99,45],[99,46,99,48],[98,61,98,63],[98,64,98,66],[99,7,99,9],[99,10,99,12],[99,13,99,15],[99,16,99,18],[99,19,99,21],[99,22,99,24],[99,25,99,27],[99,28,99,30],[98,43,98,45],[98,46,98,48],[98,49,98,51],[98,52,98,54],[98,55,98,57],[98,58,98,60],[98,25,98,27],[98,28,98,30],[98,31,98,33],[98,34,98,36],[98,37,98,39],[98,40,98,42],[98,7,98,9],[98,10,98,12],[98,13,98,15],[98,16,98,18],[98,19,98,21],[98,22,98,24],[97,49,97,51],[97,52,97,54],[97,55,97,57],[97,58,97,60],[97,61,97,63],[97,64,97,66],[97,31,97,33],[97,34,97,36],[97,37,97,39],[97,40,97,42],[97,43,97,45],[97,46,97,48],[96,61,96,63],[96,64,96,66],[97,7,97,9],[97,10,97,12],[97,13,97,15],[97,16,97,18],[97,19,97,21],[97,22,97,24],[97,25,97,27],[97,28,97,30],[96,43,96,45],[96,46,96,48],[96,49,96,51],[96,52,96,54],[96,55,96,57],[96,58,96,60],[96,25,96,27],[96,28,96,30],[96,31,96,33],[96,34,96,36],[96,37,96,39],[96,40,96,42],[96,7,96,9],[96,10,96,12],[96,13,96,15],[96,16,96,18],[96,19,96,21],[96,22,96,24],[95,49,95,51],[95,52,95,54],[95,55,95,57],[95,58,95,60],[95,61,95,63],[95,64,95,66],[95,31,95,33],[95,34,95,36],[95,37,95,39],[95,40,95,42],[95,43,95,45],[95,46,95,48],[94,61,94,63],[94,64,94,66],[95,7,95,9],[95,10,95,12],[95,13,95,15],[95,16,95,18],[95,19,95,21],[95,22,95,24],[95,25,95,27],[95,28,95,30],[94,43,94,45],[94,46,94,48],[94,49,94,51],[94,52,94,54],[94,55,94,57],[94,58,94,60],[94,25,94,27],[94,28,94,30],[94,31,94,33],[94,34,94,36],[94,37,94,39],[94,40,94,42],[94,7,94,9],[94,10,94,12],[94,13,94,15],[94,16,94,18],[94,19,94,21],[94,22,94,24],[93,49,93,51],[93,52,93,54],[93,55,93,57],[93,58,93,60],[93,61,93,63],[93,64,93,66],[93,31,93,33],[93,34,93,36],[93,37,93,39],[93,40,93,42],[93,43,93,45],[93,46,93,48],[92,61,92,63],[92,64,92,66],[93,7,93,9],[93,10,93,12],[93,13,93,15],[93,16,93,18],[93,19,93,21],[93,22,93,24],[93,25,93,27],[93,28,93,30],[92,43,92,45],[92,46,92,48],[92,49,92,51],[92,52,92,54],[92,55,92,57],[92,58,92,60],[92,25,92,27],[92,28,92,30],[92,31,92,33],[92,34,92,36],[92,37,92,39],[92,40,92,42],[92,7,92,9],[92,10,92,12],[92,13,92,15],[92,16,92,18],[92,19,92,21],[92,22,92,24]],"merged_total":2804,"flags":["merged_cut"]}
["Адмиралтейский район"]
["Район","Код","Заказчик","Титул\nАдрес","Дата начала","Дата завершения","<"," 4 кв.  2025",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2028,null,null,null,null,null,null,null,null,null,null,null,2029,null,null,null,null,null,null,null,null,null,null,null,">"]
[null,null,null,null,null,null,null,1,null,null,2,null,null,3,null,null,4,null,null,5,null,null,6,null,null,7,null,null,8,null,null,9,null,null,10,null,null,11,null,null,12]
["Адмиралтейский",76313,"СПб ГКУ Дирекция заказчика","Подольская ул, д.1-3-5\nадмиралтейский р-н, подольская ул, д.1-3-5, корп.а, кв.-","2023-04-16","2030-10-14","█","████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",76325,"СПб ГКУ Дирекция заказчика","6-я Красноармейская ул, д.15\nадмиралтейский р-н, 6-я красноармейская ул, д.15, корп.а, кв.-","2023-04-16","2030-10-14","█","████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",76321,"СПб ГКУ Дирекция заказчика","7-я Красноармейская ул, д.7\nадмиралтейский р-н, 7-я красноармейская ул, д.7, корп.а, кв.-","2023-04-16","2030-10-14","█","████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",78055,"СПб ГБУ Мостотрест","спб, адмиралтейский район, наб.реки мойки ниже матвеева моста, левы\nадмиралтейский район, набережная реки мойки нижи матвеева моста, левый берег","2023-08-01","2026-10-15","█","████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100747,"НО ФКР МКД СПБ","9-я Красноармейская ул., д. 8 литера А\n9-я Красноармейская ул., д. 8 литера А","2024-02-01","2026-04-30","█","████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",71463,"СПб ГКУ Дирекция заказчика","Марата ул, д.22-24\nадмиралтейский р-н, марата ул, д.22-24, кв.-","2024-02-01","2027-05-15","█","████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100102,"СПб ГКУ Дирекция заказчика","Галерная улица, дом 15, литера А\nГалерная улица, дом 15, литера А","2024-05-01","2030-10-14","█","████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",75825,"СПб ГКУ Управление заказчика","адмиралтейский р-н, пер. бойцова, д. 4 (производство земляных работ\nпер. бойцова, д. 4","2025-01-20","2026-07-31",null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",75827,"СПб ГКУ Управление заказчика","адмиралтейский р-н, наб. реки фонтанки, д. 135 (производство землян\nнаб. реки фонтанки, д. 135","2025-01-20","2026-07-31",null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",75904,"СПб ГКУ Управление заказчика","адмиралтейский р-н, наб. реки мойки, д. 92  (производство земляных\nнаб. реки мойки, д. 92","2025-01-20","2026-07-31",null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",75908,"СПб ГКУ Управление заказчика","большая подьяческая, д. 22 (производство земляных работ при работах\nбольшая подьяческая, д. 22","2025-01-20","2026-07-31",null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",76085,"СПб ГКУ Управление заказчика","адмиралтейский р-н, ул. декабристов, д. 14/7 (производство земляных\nул. декабристов, д. 14/7","2025-01-20","2026-07-31",null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",76088,"СПб ГКУ Управление заказчика","пер. антоненко, д. 3 (производство земляных работ при работах на ин\nпер. антоненко, д. 3","2025-01-20","2026-07-31",null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",75816,"СПб ГКУ Управление заказчика","адмиралтейский р-н, гороховая ул., д. 41 (производство земляных раб\nгороховая ул., д. 41","2025-01-20","2026-10-10",null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",75820,"СПб ГКУ Управление заказчика","адмиралтейский р-н, пер. гривцова, д. 20 (производство земляных раб\nпер. гривцова, д. 20","2025-01-20","2026-10-10",null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",75821,"СПб ГКУ Управление заказчика","адмиралтейский р-н, сенная пл., д. 3 (производство земляных работ п\nсенная пл., д. 3","2025-01-20","2026-10-10",null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",75961,"СПб ГКУ Управление заказчика","казанская ул., д. 50 (производство земляных работ при работах на ин\nказанская ул., д. 50","2025-01-20","2026-10-10",null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",76104,"СПб ГКУ Управление заказчика","казанская ул., д. 41 (производство земляных работ при работах на ин\nказанская ул., д. 41","2025-01-20","2026-10-10",null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",76106,"СПб ГКУ Управление заказчика","казанская ул., д. 43 (производство земляных работ при работах на ин\nказанская ул., д. 43","2025-01-20","2026-10-10",null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100698,"НО ФКР МКД СПБ","12-я Красноармейская ул., д. 15 литера В\n12-я Красноармейская ул., д. 15 литера В","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100703,"НО ФКР МКД СПБ","13-я Красноармейская ул., д. 22 литера А\n13-я Красноармейская ул., д. 22 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100745,"НО ФКР МКД СПБ","5-я Красноармейская ул., д. 13 литера А\n5-я Красноармейская ул., д. 13 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100746,"НО ФКР МКД СПБ","7-я Красноармейская ул., д. 20 литера А\n7-я Красноармейская ул., д. 20 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100749,"НО ФКР МКД СПБ","Б. Казачий пер., д. 9 литера Г\nБ. Казачий пер., д. 9 литера Г","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100751,"НО ФКР МКД СПБ","Большая Подьяческая ул., д. 22 литера Б\nБольшая Подьяческая ул., д. 22 литера Б","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100753,"НО ФКР МКД СПБ","Большая Подьяческая ул., д. 4 литера Б\nБольшая Подьяческая ул., д. 4 литера Б","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100754,"НО ФКР МКД СПБ","Бородинская ул., д. 13 литера А\nБородинская ул., д. 13 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100755,"НО ФКР МКД СПБ","Бронницкая ул., д. 19 литера А\nБронницкая ул., д. 19 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100775,"НО ФКР МКД СПБ","Верейская ул., д. 23 литера А\nВерейская ул., д. 23 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100776,"НО ФКР МКД СПБ","Витебская ул., д. 16 литера А\nВитебская ул., д. 16 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100777,"НО ФКР МКД СПБ","Гражданская ул., д. 9 литера А\nГражданская ул., д. 9 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100778,"НО ФКР МКД СПБ","Грибоедова наб.кан., д. 148-150 литера А\nГрибоедова наб.кан., д. 148-150 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100779,"НО ФКР МКД СПБ","Казанская ул., д. 41 литера В\nКазанская ул., д. 41 литера В","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100780,"НО ФКР МКД СПБ","Канонерская ул., д. 25 литера А\nКанонерская ул., д. 25 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100784,"НО ФКР МКД СПБ","Лермонтовский пр., д. 48 литера А\nЛермонтовский пр., д. 48 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100785,"НО ФКР МКД СПБ","Лермонтовский пр., д. 8А литера А\nЛермонтовский пр., д. 8А литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100786,"НО ФКР МКД СПБ","Малодетскосельский пр., д. 36 литера А, д. 38 литера Б\nМалодетскосельский пр., д. 36 литера А, д. 38 литера Б","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100806,"НО ФКР МКД СПБ","Можайская ул., д. 3-5 литера А\nМожайская ул., д. 3-5 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100807,"НО ФКР МКД СПБ","Можайская ул., д. 37-39 литера А\nМожайская ул., д. 37-39 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100808,"НО ФКР МКД СПБ","Мясная ул., д. 18 литера А\nМясная ул., д. 18 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100809,"НО ФКР МКД СПБ","Нарвский пр., д. 29 литера А\nНарвский пр., д. 29 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100811,"НО ФКР МКД СПБ","Подольская ул., д. 15 литера А\nПодольская ул., д. 15 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100812,"НО ФКР МКД СПБ","Подольская ул., д. 30-32 литера А\nПодольская ул., д. 30-32 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100813,"НО ФКР МКД СПБ","Подольская ул., д. 34 литера А\nПодольская ул., д. 34 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100814,"НО ФКР МКД СПБ","Фонтанки реки наб., д. 110 литера Б\nФонтанки реки наб., д. 110 литера Б","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100815,"НО ФКР МКД СПБ","Фонтанки реки наб., д. 187 литера А\nФонтанки реки наб., д. 187 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100816,"НО ФКР МКД СПБ","Фонтанки реки наб., д. 97 литера А\nФонтанки реки наб., д. 97 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101239,"НО ФКР МКД СПБ","Казначейская ул., д. 9/11 литера А\nКазначейская ул., д. 9/11 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101266,"НО ФКР МКД СПБ","Рижский пр., д. 52 литера А\nРижский пр., д. 52 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101309,"НО ФКР МКД СПБ","Фонтанки реки наб., д. 103 литера А\nФонтанки реки наб., д. 103 литера А","2025-02-01","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",78554,"НО ФКР МКД СПБ","санкт-петербург, адмиралтейский р-н, рузовская ул., д. 25, лит. а.\nсанкт-петербург г, адмиралтейский р-н, рузовская ул, д.25, корп.литера а, кв.-","2025-02-20","2026-04-30",null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101206,"НО ФКР МКД СПБ","12-я Красноармейская ул., д. 11 литера А\n12-я Красноармейская ул., д. 11 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101208,"НО ФКР МКД СПБ","12-я Красноармейская ул., д. 13 литера А, литера Б\n12-я Красноармейская ул., д. 13 литера А, литера Б","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101209,"НО ФКР МКД СПБ","13-я Красноармейская ул., д. 24 литера А\n13-я Красноармейская ул., д. 24 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101212,"НО ФКР МКД СПБ","Б. Морская ул., д. 56 литера А\nБ. Морская ул., д. 56 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101213,"НО ФКР МКД СПБ","Верейская ул., д. 15 литера А, литера Б\nВерейская ул., д. 15 литера А, литера Б","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101214,"НО ФКР МКД СПБ","Верейская ул., д. 22-24, литера А\nВерейская ул., д. 22-24, литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101215,"НО ФКР МКД СПБ","Витебская ул., д. 25 литера А\nВитебская ул., д. 25 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101216,"НО ФКР МКД СПБ","Витебская ул., д. 25 литера Б\nВитебская ул., д. 25 литера Б","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101217,"НО ФКР МКД СПБ","Гражданская ул., д. 7 литера А\nГражданская ул., д. 7 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101229,"НО ФКР МКД СПБ","Грибоедова наб.кан., д. 109/8 литера А, Б\nГрибоедова наб.кан., д. 109/8 литера А, Б","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101230,"НО ФКР МКД СПБ","Гривцова пер., д. 8 литера А\nГривцова пер., д. 8 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101231,"НО ФКР МКД СПБ","Гривцова пер., д. 9 литера А, литера Б, литера В\nГривцова пер., д. 9 литера А, литера Б, литера В","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101232,"НО ФКР МКД СПБ","Декабристов ул., д. 48 литера А\nДекабристов ул., д. 48 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101233,"НО ФКР МКД СПБ","Декабристов ул., д. 51, литера А\nДекабристов ул., д. 51, литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101235,"НО ФКР МКД СПБ","Декабристов ул., д. 51, литера В\nДекабристов ул., д. 51, литера В","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101237,"НО ФКР МКД СПБ","Измайловский пр., д. 31 литера А\nИзмайловский пр., д. 31 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101238,"НО ФКР МКД СПБ","Измайловский пр., д. 31 литера Д\nИзмайловский пр., д. 31 литера Д","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101241,"НО ФКР МКД СПБ","Климов пер., д. 5 литера А\nКлимов пер., д. 5 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101242,"НО ФКР МКД СПБ","Климов пер., д. 9 литера А\nКлимов пер., д. 9 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101244,"НО ФКР МКД СПБ","Лабутина ул., д. 16 корп. 2 литера А\nЛабутина ул., д. 16 корп. 2 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101252,"НО ФКР МКД СПБ","Лермонтовский пр., д. 30 литера А\nЛермонтовский пр., д. 30 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101289,"НО ФКР МКД СПБ","Лифляндская ул., д. 8 литера А\nЛифляндская ул., д. 8 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101290,"НО ФКР МКД СПБ","Лоцманская ул., д. 6 литера А\nЛоцманская ул., д. 6 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101291,"НО ФКР МКД СПБ","Обводного канала наб., д. 203 литера А\nОбводного канала наб., д. 203 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101292,"НО ФКР МКД СПБ","Пряжки р. наб., д. 36 литера А\nПряжки р. наб., д. 36 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101293,"НО ФКР МКД СПБ","Рузовская ул., д. 33 литера А\nРузовская ул., д. 33 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101297,"НО ФКР МКД СПБ","Садовая ул., д. 81 литера А\nСадовая ул., д. 81 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101298,"НО ФКР МКД СПБ","Садовая ул., д. 85 литера А\nСадовая ул., д. 85 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101299,"НО ФКР МКД СПБ","Серпуховская ул., д. 20 литера А\nСерпуховская ул., д. 20 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101301,"НО ФКР МКД СПБ","Союза Печатников ул., д. 7 литера А\nСоюза Печатников ул., д. 7 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101304,"НО ФКР МКД СПБ","Троицкий пр., д. 5 литера А\nТроицкий пр., д. 5 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101305,"НО ФКР МКД СПБ","Фонтанки реки наб., д. 139 литера А\nФонтанки реки наб., д. 139 литера А","2025-03-01","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",82597,"СПб ГБУ Мостотрест","г. санкт-петербург, адмиралтейский район, набережная адмиралтейског\nадмиралтейский район, набережнаяадмиралтейского канала от площади труда до 1-го мостакруштейна","2025-03-01","2026-07-15",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",82508,"СПб ГБУ Мостотрест","г. санкт-петербург, адмиралтейский район, мост декабристов (офицерс\nг.  адмиралтейский район, мост декабристов (офицерский мост)","2025-03-01","2027-04-15",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101193,"СПб ГКУ Дирекция заказчика","Угловой переулок, дом 11, литера А\nУгловой переулок, дом 11, литера А","2025-03-03","2030-10-14",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101262,"СПб ГКУ Дирекция заказчика","Английский проспект, дом 8-10, литера А\nАнглийский проспект, дом 8-10, литера А","2025-03-03","2035-10-14",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102832,"НО ФКР МКД СПБ","Бронницкая улица, дом 22, литера А\nБронницкая улица, дом 22, литера А","2025-03-05","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102839,"НО ФКР МКД СПБ","Грибоедова наб.кан., д. 81 литера А\nГрибоедова наб.кан., д. 81 литера А","2025-03-05","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102193,"НО ФКР МКД СПБ","Якубовича ул., д. 2 литера А\nЯкубовича ул., д. 2 литера А","2025-03-15","2026-04-30",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",83261,"ПАО Россети Ленэнерго","санкт-петербург, адмиралтейский р-н, наб. р. фонтанки, д. 144, лит.\nнабережная реки фонтанки, дом 144, литера б  > курляндская улица, дом 1, литера с > курляндская улиц","2025-03-17","2026-10-13",null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102079,"НО ФКР МКД СПБ","4-я Красноармейская ул., д. 16 литера А\n4-я Красноармейская ул., д. 16 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102080,"НО ФКР МКД СПБ","7-я Красноармейская ул., д. 9 литера А\n7-я Красноармейская ул., д. 9 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102081,"НО ФКР МКД СПБ","8-я Красноармейская ул., д. 21 литера Б\n8-я Красноармейская ул., д. 21 литера Б","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102082,"НО ФКР МКД СПБ","9-я Красноармейская ул., д. 21 литера А\n9-я Красноармейская ул., д. 21 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102083,"НО ФКР МКД СПБ","Английская наб., д. 48 литера Б\nАнглийская наб., д. 48 литера Б","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102084,"НО ФКР МКД СПБ","Английский пр., д. 17-19 литера Б\nАнглийский пр., д. 17-19 литера Б","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102087,"НО ФКР МКД СПБ","Б.Морская ул., д. 34 литера А\nБ.Морская ул., д. 34 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102088,"НО ФКР МКД СПБ","Батайский пер., д. 4 литера А\nБатайский пер., д. 4 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102089,"НО ФКР МКД СПБ","Бойцова пер., д. 6 литера А\nБойцова пер., д. 6 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102099,"НО ФКР МКД СПБ","Бумажная ул., д. 10 литера А\nСПб, Бумажная ул., д. 10 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102105,"НО ФКР МКД СПБ","Верейская ул., д. 13а литера А; Верейская ул., д. 13б литера А\nСПб, Верейская ул., д. 13а литера А; Верейская ул., д. 13б литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102106,"НО ФКР МКД СПБ","Верейская ул., д. 28 литера А\nВерейская ул., д. 28 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102108,"НО ФКР МКД СПБ","Верейская ул., д. 42/8 литера А\nВерейская ул., д. 42/8 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102109,"НО ФКР МКД СПБ","Верейская ул., д. 8 литера А\nВерейская ул., д. 8 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102110,"НО ФКР МКД СПБ","Галерная ул., д. 49 литера А\nГалерная ул., д. 49 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102111,"НО ФКР МКД СПБ","Галерная ул., д. 28 литера В\nГалерная ул., д. 28 литера В","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102112,"НО ФКР МКД СПБ","Галерная ул., д. 56 литера Б\nГалерная ул., д. 56 литера Б","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102114,"НО ФКР МКД СПБ","Грибоедова наб. кан., д. 102, литера Б\nГрибоедова наб. кан., д. 102, литера Б","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102117,"НО ФКР МКД СПБ","Крюкова канала наб., д. 15 литера А\nКрюкова канала наб., д. 15 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102123,"НО ФКР МКД СПБ","Пряжки р. наб., д. 28 литера Б; Пряжки р. наб., д. 28 литера В\nПряжки р. наб., д. 28 литера Б; Пряжки р. наб., д. 28 литера В","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102124,"НО ФКР МКД СПБ","Пряжки р. наб., д. 50 литера А\nПряжки р. наб., д. 50 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102125,"НО ФКР МКД СПБ","Псковская ул., д. 7 литера А\nПсковская ул., д. 7 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102126,"НО ФКР МКД СПБ","Садовая ул., д. 122, литера Б\nСадовая ул., д. 122, литера Б","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102127,"НО ФКР МКД СПБ","Садовая ул., д. 96 литера А\nСадовая ул., д. 96 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102128,"НО ФКР МКД СПБ","Старо-Петергофский пр., д. 21 литера Е\nСтаро-Петергофский пр., д. 21 литера Е","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102129,"НО ФКР МКД СПБ","Фонарный пер., д. 14 литера А\nФонарный пер., д. 14 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102406,"НО ФКР МКД СПБ","Измайловский пр., д. 11 литера А\nИзмайловский пр., д. 11 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102407,"НО ФКР МКД СПБ","Лермонтовский пр., д. 12 литера А\nЛермонтовский пр., д. 12 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102408,"НО ФКР МКД СПБ","Можайская ул., д. 33 литера А\nМожайская ул., д. 33 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102409,"НО ФКР МКД СПБ","Московский пр., д. 45 литера Б\nМосковский пр., д. 45 литера Б","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102412,"НО ФКР МКД СПБ","Нарвский пр., д. 19 литера А\nНарвский пр., д. 19 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102414,"НО ФКР МКД СПБ","Обводного канала наб., д. 165 литера Б\nОбводного канала наб., д. 165 литера Б","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102417,"НО ФКР МКД СПБ","Перекопская ул., д. 1 литера А\nПерекопская ул., д. 1 литера А","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102480,"НО ФКР МКД СПБ","Канонерская ул., д. 29 литера В\nКанонерская ул., д. 29 литера В","2025-04-01","2026-04-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",71149,"СПб ГБУ Ленсвет","санкт-петербург, юсуповский сад, участок 1, (между садовой ул. и д.\nсад дворца Юсуповых (г. СПб, Юсуповский сад, участок 1, между Садовой ул. и д. 117 лит. А по наб. реки Фонтанки)","2025-04-15","2026-07-30",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",100992,"Комитет по благоустройству","Бульвар б/н на ул. Циолковского от наб. р. Фонтанки до наб. Обводного кан.\nБульвар б/н на ул. Циолковского от наб. р. Фонтанки до наб. Обводного кан. Благоустройство объектов зеленых насаждений, расположенных на территориях зеленых насаждений общего пользования городского значения","2025-04-15","2026-10-14",null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",75962,"СПб ГКУ Управление заказчика","казначейская ул., д. 5 (производство земляных работ при работах на\nказначейская ул., д. 5","2025-05-01","2026-10-10",null,null,null,null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",75963,"СПб ГКУ Управление заказчика","адмиралтейский р-н, казначейская ул., д. 13 (производство земляных\nказначейская ул., д. 13","2025-05-01","2026-10-10",null,null,null,null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",75965,"СПб ГКУ Управление заказчика","адмиралтейский р-н, наб. реки фонтанки, д. 109 (производство землян\nнаб. реки фонтанки, д. 109","2025-05-01","2026-10-10",null,null,null,null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",79157,"СПб ГКУ Управление заказчика","санкт-петербург, адмиралтейский р-н, квартал (рижский пр. -  старо-\nквартал (рижский пр. -  старо-петергофский пр. - курляндская ул. - ул. степана разина)","2025-05-01","2026-10-10",null,null,null,null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102131,"Комитет по благоустройству","Выполнение работ по художественно-ландшафтному оформлению Исаакиевской площади\nИсаакиевская площадь","2025-05-15","2027-10-14",null,null,null,null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",101190,"ГУП Водоканал СПб","СПб, Парфёновская ул. (напротив д.108 по наб.Обводного канала)\nСПб, Парфёновская ул. (напротив д.108 по наб.Обводного канала)","2025-06-01","2026-05-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",82596,"СПб ГБУ Мостотрест","спб, адмиралтейский район, наб. канала грибоедова от харламова мост\nадмиралтейский район, набережная каналагрибоедова от харламова моста до ново-никольского моста,п","2025-06-01","2027-10-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",82146,"СПб ГБУ Ленсвет","санкт-петербург, адмиралтейский р-н, дерптский сквер. производство\nкорректировка сроков производства работ по ключу: 73887 по адресу:  адмиралтейский район, дерптский","2025-07-01","2026-05-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",105393,"ООО Петербурггаз","Ремонт оборудования ГРП№50\nСПб., Центральный р-н, наб. р. Мойки д.126, к. 3, лит. Ф","2025-09-15","2026-10-05",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",80757,"СПб ГКУ Дирекция транспортного строительства","капитальный ремонт ул.якубовича. для изменения сроков производства\nкапитальный ремонт ул.якубовича. для изменения сроков производства работ по ключу 76933","2025-10-01","2027-10-14",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",105340,"СПб ГКУ Дирекция транспортного строительства","Ремонт трамвайных путей\nСадовая ул. от Тургенева до Мало-Калинкина моста, включительно Мало-Калинкин мост","2025-10-10","2027-10-14",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]
["Адмиралтейский",102888,"ГУП Водоканал СПб","Санкт-Петербург, Смоленская улица, дом 14, литера А (ДПС)\nСанкт-Петербург, Смоленская улица, дом 14, литера А (ДПС)","2025-11-30","2026-10-14",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"████",null,null,"████",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"█"]